RATAL GROUP

Travel Agency & Corporate Management System

UNIFIED SYSTEM REQUIREMENTS

Version 8.0  |  Combined Edition  |  July 2026  |  CONFIDENTIAL

Author: Mahmood Shahbaz

PART ONE: System Requirements (Sections 1–28 + Appendices A–B)

PART TWO: Site Master & Budget vs Actual Framework (All 10 Questions Resolved)

Go-Live Target: July 31, 2026 (Phase 1)

PART ONE

SYSTEM REQUIREMENTS

Sections 1–28 + Appendices A & B  |  Version 7.0 Content

# Design Principles & Technology Stack

| Principle | Rule |
| --- | --- |
| Single Entry | No data entered twice. Field team → System → Accounts — one flow. |
| Form Design | Every form at its own URL. Mobile-friendly, shareable via Telegram/WhatsApp, any device. |
| Dashboard | Every user sees ONLY what their role + entity permit. Role + Entity determines all visible data. |
| Stack | React + Vite ¦ Supabase (PostgreSQL + RLS) ¦ Digital Ocean |
| Language | Arabic (RTL) + English — toggle on every screen |
| Notifications | Telegram Bot (@RatalGroupBot) — FREE |
| ZATCA | Phase 1 QR codes (live) ¦ Phase 2 clearance (post go-live) |
| Go-Live | July 31, 2026 — Phase 1 only |

| Entity | Full Name | Theme Colour |
| --- | --- | --- |
| RAT | Ratal Tours and Travels | Blue #1565C0 |
| GWT | Green Wings Travel | Green #2E7D32 |
| ACCSYS | Ratal Advanced Technologies | Purple #5A32D4 |

# Section 1 — Module Map by Entity

## 1.1  Common to All 3 Entities

Login & User Roles (entity-aware, role-aware)

Dashboard (entity-specific KPIs, role-filtered layout)

Employee Engagement (mandatory — all staff, all locations)

Employees | Payroll (cash/bank split, GOSI, loans, penalties, OT) | EOS

Invoices (ZATCA Phase 1 QR) | Payments & Receipts | Chart of Accounts / General Ledger

Journal Vouchers | Contra Vouchers | Day Book | VAT Summary (quarterly + yearly GAZT export)

Compliance Alerts (Iqama, Passport, QIWA, SCE, Vehicles, CR, GOSI, Municipality, CITC, Ministry)

Telegram Notifications | Reports

## 1.2  RAT + GWT — Travel Agency Modules

Air Tickets (manual entry + Amadeus CSV import)

Customers | Airlines | IATA / BSP | BSP Payments | Refunds & Credit Notes

Hotels / Car Rentals / Resorts  [Phase 2]

Customer Balances | Statement of Account

16 Travel Sales Reports (from Mr. Hamdi's COBOL system)

Business Trip Expense Tracking

## 1.3  ACCSYS — Corporate Modules

Customers (STC, Mobily, Zain, Ministries, Banks) | Contractors (Nokia, Cisco, Huawei, ZTE, SBM, BMC, MIS)

Projects | Jobs (within Projects) | Job Activator

Site Master — Budget vs Actual per Job/Site  ★ NEW (see Part Two for full specification)

Internal Purchase Orders (ACC-PO-XXXX outgoing series)

Money Requests (8-stage workflow) | PM Budget Planning

Supplier PO Management | Sub-contractor Management | Vendor/Party List

Expenses | Food Allowance | Overtime | Business Trip | Department Statements (15 types)

## 1.4  Field Team Apps (ACCSYS — Mobile URLs)

Expense Submission (Job Activator — Site# auto-fills Project# and Job#)

Food Allowance | Overtime | Car Maintenance Request

Site Survey [Phase 2 — enterprise version] | Site Status / Installation Progress

GPS Attendance | Employee Engagement (mandatory)

# Section 2 — Authentication, User Roles & Dashboard Access

## 2.1  User Role Matrix

| Role | Login | Entity Access | Dashboard |
| --- | --- | --- | --- |
| SuperAdmin | Email + Password | ALL 3 | Entity switcher. All KPIs all entities. |
| Admin / Accounts | Email + Password | Own entity | Full entity dashboard. All modules. |
| Department Head | Email + Password | Own entity | Dept-filtered: pending approvals, dept projects, dept spend. |
| Project Manager | Email + Password | Own entity | Own projects + jobs. Money Request form. |
| Travel Agent | Email + Password | Own entity | Tickets, Customers, BSP, Refunds, Reports only. |
| Field Employee | Mobile + Session | Own entity | Mobile: own submissions only. Submit forms only. |

Data Segregation: All filtering enforced via Supabase Row-Level Security (RLS). Users never see cross-entity data.

## 2.2  Money Request — 8-Stage Workflow

| Stage | Status | Action | Notification |
| --- | --- | --- | --- |
| 1 — Request | DH_PENDING | PM/DH creates MR with line items (LineType, Contractor, ProjectNo, JobNo, SiteNo, IBAN, Amount) | → Dept Head |
| 2 — DH Approval | FIN_PENDING / REJECTED | DH approves or rejects | Approved → Accounts ¦ Rejected → Requestor |
| 3 — Accounts View | FIN_PENDING | Consolidated dashboard grouped Dept → Project | — |
| 4 — Supplier Payment | SUPPLIER_PMT_REQUESTED | Accounts pays supplier for SUPPLIER_PAYMENT lines | — |
| 5 — Funds Sent | FUNDS_SENT | Transfer: ANB-77 (TISU) or ANB-39 (NISU/ITSU/CISU). Auto Contra Voucher. | → DH (RECEIVING) |
| 6 — Distribution | DISTRIBUTION | Dept distributes to employees/small suppliers | Employee marks RECEIVED |
| 7 — Supplier Complete | SUPPLIER_PMT_COMPLETED | After direct supplier payment confirmed | — |
| 8 — Closed | CLOSED | All lines settled and reconciled | — |

## 2.3  Forms — Separate Window Design

Every form opens at its own dedicated URL, shareable via Telegram/WhatsApp. Works on any mobile browser without app installation. After submission: shows Request# and Telegram confirmation.

Form URLs: /forms/expense | /forms/food-allowance | /forms/overtime | /forms/money-request | /forms/car-maintenance | /forms/po-request

## 2.4  Field Staff Authentication

First login (once per device): Mobile# + last 4 digits as PIN → 30-day session token. Every subsequent visit: opens URL, sees name, taps Enter — auto-login. Admin can revoke any session. Token bound to device fingerprint.

# Section 3 — Departments

| Code | Full Name | Entity |
| --- | --- | --- |
| NISU | Network Infrastructure Services Unit | ACCSYS |
| TISU | Tower Infrastructure Services Unit | ACCSYS |
| CISU | Civil Infrastructure Services Unit | ACCSYS |
| ITSU | IT Services Unit | ACCSYS |
| OFFICE | Office / Administration | ACCSYS |
| TRAVELS | Travel Team | RAT / GWT |
| SAUDIS | Saudi Nationals | ALL |
| ACCOUNTS | Finance / Accounts Department | ALL |

# Section 4 — Employee Database

## 4.1  Employee Categories

| Category | Description | Payroll Method | Loan Eligible |
| --- | --- | --- | --- |
| Ratal Sponsored | Under Ratal Iqama | Cash + Bank split | YES |
| TRAVELS | Travel agency staff | Cash + Bank split | YES |
| SAUDIS | Saudi nationals | Full Bank only | NO |
| Outsource | Not under Ratal Iqama | Full Cash only | NO |

## 4.2  Key Employee Fields

| Field | Type / Enum | Notes |
| --- | --- | --- |
| EmployeeID | Text | ACC-XXXX / RAT-XXXX / GWT-XXXX / OUT-XXXX (by entity + employee type) |
| Designation | Text | GM ¦ Dept Head ¦ Director ¦ PM ¦ Supervisor ¦ Engineer ¦ Technician ¦ Accountant ¦ etc. |
| Department | Enum | CISU/NISU/TISU/ITSU/OFFICE/TRAVELS/SAUDIS/ACCOUNTS |
| Entity | Enum | RAT / GWT / ACCSYS |
| Category | Enum | RATAL_SPONSORED / TRAVELS / SAUDIS / OUTSOURCE |
| Status | Enum | ACTIVE / INACTIVE / LEFT |
| Basic / HRA / Conveyance / Technical | Decimal SAR | Fixed salary components |
| SalaryPackage | Auto-calc | = Basic + HRA + Conveyance + Technical |
| BankPortion | Decimal SAR | Fixed amount to ANB-18. GOSI calculation base. |
| CashPortion | Auto-calc | = SalaryPackage − BankPortion |
| PaymentType | Enum | CASH_BANK / BANK_ONLY / CASH_ONLY |
| OTAllowed / FoodAllowanceEligible / LoanAllowed / HasCar / HasDependent | Boolean | Eligibility flags |
| MobileNumber | Text | Field staff login — NEVER changes |
| TelegramChatID | Text | From @RatalGroupBot activation — used for all notifications |
| NationalIDExpiry / PassportExpiry / QIWAValidity / SCEExpiry | Date | Compliance alert triggers (30 or 60 day windows) |
| IBAN | Text | SA-format 24-char IBAN — used in WPS file |
| TicketEligible / TicketCycleMonths / DefaultTicketAmount | Boolean/INT/Decimal | Air ticket benefit config (12 / 18 / 24 month cycles) |

## 4.3  Ticket Eligibility by Designation

| Designation | Cycle | Employee Amt | Family Coverage | Destination |
| --- | --- | --- | --- | --- |
| Technician | 2 years | SAR 1,600 | None | N/A |
| Senior Technician / Coordinator | 1 year | SAR 1,600 | None | N/A |
| Project Manager / Engineer | 1 year | SAR 2,000 | None | N/A |
| Department Head | 1 year | SAR 2,200 | Wife + 3 Kids | Home country |
| General Manager | 6 months | SAR 2,500 | Wife + 4 Kids | Any destination |

# Section 5 — Payroll

## 5.1  Monthly Salary Structure

| Component | Calculation | Notes |
| --- | --- | --- |
| Basic + HRA + Conveyance + Technical | Fixed per employee | Earnings |
| Overtime | Basic ÷ 30 ÷ 8 × 1.5 | Auto-pulled from approved OT submissions. Max 60 hrs/month. |
| Bonus / Other | Ad-hoc entry | Earnings |
| GROSS SALARY | Sum of all earnings |  |
| Loan EMI | Cash Portion only | Deduction |
| Penalty | Cash Portion only ¦ 10% cap | Deduction — carry-forward if over cap |
| NET SALARY | Gross − deductions |  |
| Bank Portion | Fixed SAR → ANB-18 | WPS transfer ¦ GOSI base |
| Cash Portion | Net − Bank Portion | Cash payment |

Note: Food Allowance is NOT in payroll — paid as a separate advance through FA form.

## 5.2  GOSI Rules

| Employee Type | Base | Rate | Who Pays |
| --- | --- | --- | --- |
| Saudi Nationals | Bank Portion | 9% | Company pays ALL — zero employee deduction |
| Expat Employees | Bank Portion | 3% (hazard) | Company-borne entirely |

## 5.3  Loan Rules

Eligibility: Ratal Sponsored + TRAVELS only. Max: 3 × SalaryPackage. Tenure: max 24 months. EMI from Cash Portion only. One active loan per employee. Starts next month after approval.

## 5.4  Penalties

| Type | Classification | Rule |
| --- | --- | --- |
| Employee-borne | Over-speeding, wrong parking, signal jump, phone while driving | Cash Portion only ¦ 10% cap/month ¦ Carry-forward |
| Company-borne | Plate damage, no insurance, expired registration, no MVPI | Company expense — not deducted from employee salary |

## 5.5  WPS File

Format: ANB pipe-delimited text. H (header) + D (detail per employee). Source: ANB-18. Covers Bank Portion only. Excludes Outsource. BatchRef = DDMMYYYY.001. Full spec in Appendix A.

# Section 6 — End of Service (Labour Law Art. 84)

| Scenario | EOS Base | Entitlement |
| --- | --- | --- |
| Resigned < 2 years | Basic | ZERO |
| Resigned 2–5 years | Basic | 1/3 of full EOS |
| Resigned 5–10 years | Basic | 2/3 of full EOS |
| Resigned 10+ years | Basic | Full EOS |
| Terminated / Expired / Death | Basic | Full EOS |
| 15+ years of service (any reason) | Full Salary Package | Full EOS (base auto-switches) |

Formula: First 5 years: Basic × 0.5/year (15 days). Beyond 5 years: Basic × 1.0/year (30 days). Deductions: outstanding loan balance + ticket advance + penalties.

# Section 7 — Vacations & Ticket Benefit

| Type | Max Days | In Annual 30? | Deduction |
| --- | --- | --- | --- |
| Annual | 30/year | YES | None within limit |
| Emergency | 15 once/year | NO | None |
| Sick (normal) | As needed | NO | Basic ÷ 30 per day |
| Sick (major illness) | 60 days | NO | None — paid in full |
| Unpaid Phase 1 (days 1–30 over limit) | 30 | NO | HRA + Conv + Tech deducted per day |
| Unpaid Phase 2 (days 31+ over limit) | Unlimited | NO | Full SalaryPackage ÷ 30 per day |

Note: Levy before rejoining: SAR 800/month per month of overstay. Employee MUST clear ALL levy before REJOINED status is allowed.

# Section 8 — Travel Agency (RAT + GWT)

## 8.1  Air Ticket Entry

Ticket# | Ticket Type (0=Normal/1=E/F/2=DR) | Passenger Name | Routing | Class (F/C/Y/W) | Ticket Value | Tax | Net to Carrier (auto) | Discount % | Selling Fare | Commission (auto from Airlines table) | Account# | Invoice# | Date | Agent (dropdown) | Payment Type (CASH/CREDIT)

## 8.2  VAT

| Route | VAT Rate | Notes |
| --- | --- | --- |
| DOM (Domestic) | 15% of ticket value | Applied to ticket + service fees |
| INT (International) | 0% — zero rated | Service fees: 15% VAT separately |

## 8.3  BSP & Refunds

BSP: Period | BSP# | Gross Sales | Gross Refunds | Commission | Net Remittance | Due Date | Status.

Refunds: Original Ticket# | Gross Refund | Penalty | Net Refund | VAT Refund | Credit Note# | Status.

# Section 9 — Travel Reports (RAT + GWT)

| # | Report | Filter / Output |
| --- | --- | --- |
| 1 | Airline Accounts | Airline, Date → Sales, Refund, Discount, Net |
| 2 | Chart of Accounts | Account listing |
| 3 | Daily Sales & Refund | Date → Tickets, Fares, Refunds, Net |
| 4 | Sales of an Employee | Agent, Date → count, Fares, Commission |
| 5 | Credit (CR) Report | Credit customers, Outstanding, Overdue |
| 6 | Airlines Sales Summary | All airlines → Code, Sales, Refunds, Net |
| 7 | Airlines Sales Report 1 (Normal) | Type = 0 tickets only |
| 8 | Airlines Sales Report 2 (Special) | Type = 1, 2 tickets only |
| 9 | Customer Discounts | Customer, Date → Discount%, Amount |
| 10 | General Ledger | Account → Date ¦ Particulars ¦ Dr ¦ Cr ¦ Balance |
| 11 | Print Invoices | Invoice# → full ZATCA QR invoice |
| 12 | Print Credit Notes | Credit note → full printout |
| 13 | Invoice List | Date Range → Date, Invoice#, Customer, Amount |
| 14 | Customer Balances List | All customers → Account# ¦ Name ¦ Tel ¦ Balance |
| 15 | Statement of Account | Customer → Date ¦ Details ¦ Dr ¦ Cr ¦ Balance |
| 16 | Tickets Below Margin | Set min margin → shows tickets below it |

# Section 10 — ACCSYS Corporate: Projects, Jobs & Contractor Hierarchy

## 10.1  Three-Tier Structure

| Tier | Party | Ratal's Relationship |
| --- | --- | --- |
| Tier 1 — End Customer | STC, Mobily, Zain, TAWAL, Ministries, Banks | Network owner. Sets specification. Ratal has NO direct contract with Tier 1. |
| Tier 2 — Contractor | Nokia, Huawei, Cisco, ZTE, SBM, BMC, MIS, Solutions, Mobi Serve, Ericsson, Juniper | Issues POs to Ratal. RATAL INVOICES THIS TIER ONLY — referencing Contractor PO#. |
| Tier 3 — Ratal ACCSYS | Ratal Group (Sub-Contractor) | Executes field delivery. Issues ACC-PO-XXXX outward to sub-cons and suppliers. |

## 10.2  Department → Contractor Mapping

| Department | Works With (Contractors) | For (End Clients) |
| --- | --- | --- |
| NISU | Solutions, Cisco, Nokia, Huawei | STC, Mobily, Zain, Ministries |
| TISU | Nokia, ZTE, Huawei, Mobi Serve, Shbakath | STC, Mobily, Zain, Ministries |
| CISU | SBM, ZTE, Huawei, Nokia | STC, Mobily, Zain, Ministries |
| ITSU | MIS, BMC | STC |

✔  CONFIRMED: Invoice always references Contractor PO# — not End Customer Job#. End Customer Job# stored as additional reference only.

## 10.3  Projects DB — Key Fields

| Field | Notes |
| --- | --- |
| ProjectNo | Auto-generated: P-YY001 (e.g. P-26001). Read-only once created. |
| Department | NISU / TISU / CISU / ITSU |
| ContractorID + EndCustomerID | FK to Party List (Contractor type) and Customers table |
| ContractorPONo / PODate / POValue (SAR) | REQUIRED — the revenue reference document for this project |
| EndCustomerRef | OPTIONAL — end client Job# / RFC# for cross-referencing |
| Status | OPEN / ACTIVE / ON_HOLD / COMPLETED / CLOSED / INACTIVE / CANCELLED |
| PM + Supervisor | From employee list. One PM/Supervisor can be on multiple projects. |
| Contractor PM Name / Mobile / Email | ALL MANDATORY — contractor's project contact person |
| ContractValue (SAR) | No maximum — up to SAR 99M+ |
| StartDate / EndDate | DD/MM/YYYY display format |

## 10.4  Budget vs Actual (Project Level)

| Metric | Formula |
| --- | --- |
| Total Cost | Team Expenses + Supplier POs + Sub-Con POs + Material + Food + OT + Petty Cash |
| Revenue (Invoiced) | Sum of all invoices raised against Contractor POs for this project |
| MARGIN | ContractorPOValue − Total Cost |
| MARGIN % | Margin ÷ ContractorPOValue × 100 |

Note: Site Master (Part Two) provides a deeper site-level Budget vs Actual with budget locking, milestone gating, and traffic light alerts at 70/85/95/100% of budget.

# Section 11 — Field Team Apps (ACCSYS)

## 11.1–11.3  Submission Forms

| Form | URL | Key Auto-fills / Gate |
| --- | --- | --- |
| Expense | /forms/expense | Job Activator: Site# → Project#, Job#, Contractor auto-filled. Telegram ack on submit. |
| Food Allowance | /forms/food-allowance | Gate: FoodAllowanceEligible = YES AND Location = REMOTE. Rate: SAR 30 or SAR 20/day. |
| Overtime | /forms/overtime | Gate: OTAllowed = YES AND monthly hours < 60. Rate: Basic ÷ 30 ÷ 8 × 1.5. Auto-calculated. |
| Car Maintenance | /forms/car-maintenance | Submits to DH → Accounts → RECEIVING + EXPENSE by employee. |

## 11.4  Site Status Stages

PENDING → MOBILISED → IN_PROGRESS → MATERIAL_WAITING → COMPLETED → SNAGGING → HANDED_OVER → INVOICED

## 11.5  GPS Site Registration

First visit: Employee shares Telegram GPS → creates UNCONFIRMED record. Next 2 visits within 500m → GPS averaged and LOCKED (CONFIRMED). Admin can enter Google Maps coordinates directly (ADMIN_CONFIRMED).

# Section 12 — Accounting (All Entities)

Core Principle: Every transaction auto-posts to the ledger. No manual double-entry.

## 12.1  Ledger Categories

| Category | Code Range | Key Accounts |
| --- | --- | --- |
| BANK | ANB-xx | ANB-15 (ACCSYS) ¦ ANB-77 (TISU) ¦ ANB-39 (NISU/ITSU/CISU) ¦ ANB-18 (WPS) ¦ ANB-29 (RAT) ¦ ANB-11 (GWT) |
| CASH | CASH-xxx | CASH-001 Main Petty Cash |
| EXPENSE | EXP-xxx | EXP-001 Government ¦ EXP-002 External ¦ EXP-003 Employee ¦ EXP-004 SubCon |
| INTERNAL | INT-xxx | Adjustments ¦ Inter-Bank ¦ Suspense ¦ Advance Paid ¦ Advance Received |
| CLEARING | CLR-xxx | CLR-001 Ahmed ¦ CLR-002 Rashad |
| GOVERNMENT | GOV-xxx | Iqama ¦ Levy ¦ CR ¦ Visa ¦ VAT Input/Output ¦ GOSI ¦ Zakat |
| CUSTOMER / SUPPLIER / SUBCON / CONTRACTOR | CUS/SUP/SCN/CON-xxx | One account per party |
| EMPLOYEE | EMP-xxx | One per employee (e.g. EMP-0002 Mahmood Shahbaz) |

## 12.2  Core Transaction Types

| Type | Auto-Posts To | Key Linkages |
| --- | --- | --- |
| Journal Voucher | Both ledgers simultaneously | Dept ¦ ProjectNo ¦ JobNo ¦ ContractorID ¦ VATType |
| Contra Voucher | Both bank ledgers | Inter-entity ANB-15 → ANB-77 / ANB-39 / ANB-18 transfers |
| Payment (Outgoing) | Payee ledger + Bank/Cash | PayeeCategory ¦ ExpenseType ¦ Site Master # (new) |
| Receipt (Incoming) | Customer ledger + Bank/Cash | CustomerPO ¦ Receipt Allocation (lump → multiple invoices) |
| Invoice (ACCSYS) | Contractor ledger | ContractorPONo (REQUIRED) ¦ Site Master # ¦ ZATCA QR |

Note: ACCSYS payment bank rule: ANB-15, ANB-39, or ANB-77 only. RAT/GWT accounts not available in ACCSYS forms.

# Section 13 — Department Statements (ACCSYS)

| Statement | Filters |
| --- | --- |
| Employee Statement — Salaries | Employee ¦ Dept ¦ Month |
| Employee Statement — Expenses | Employee ¦ Dept ¦ Project ¦ Job ¦ Month |
| Department Statement — Projects / Jobs / Expenses / Revenue / Vendors / Sub-Cons | Dept + relevant filters |
| Contractor Statement | Contractor ¦ Dept ¦ Period — consolidated across all Nokia/Huawei etc. projects |
| Customer Statement (End Clients) | End Customer ¦ Contractor ¦ Dept ¦ Period |
| Job Cost Summary | Job# ¦ Budget vs Actual all categories |
| Site Master P&L (★ NEW) | Site Master ID ¦ Unit ¦ Project ¦ Date Range — see Part Two |

# Section 14 — Invoices & ZATCA

| Phase | Status | Details |
| --- | --- | --- |
| Phase 1 — QR Codes | LIVE | TLV Base64 QR: Seller ¦ VAT# ¦ DateTime ¦ Total (incl. VAT) ¦ VAT Amount. Shared VAT# all 3 entities. |
| Phase 2 — Clearance | Post Go-Live | Real-time ZATCA API. Currently ENZAPPs. Migrate after stabilisation. |

Types: TAX INVOICE | SIMPLIFIED TAX INVOICE | CREDIT NOTE

# Section 15 — Compliance Alerts

| Category | Document | Alert Window | Visible To |
| --- | --- | --- | --- |
| Employee | Iqama / National ID | 30 days | Admin + Accounts |
| Employee | Passport | 60 days | Admin + Accounts |
| Employee | Health Insurance | 30 days | Admin + Accounts |
| Employee | QIWA Validity | 30 days | Admin + Accounts |
| Employee | SCE Certificate | 60 days | Admin |
| Vehicle | Insurance / MVPI / Registration | 30 days | Admin + Accounts |
| Company | CR ¦ GOSI ¦ Municipality ¦ Baladiya ¦ CITC ¦ Ministry | 30–60 days | Admin + Accounts |

# Section 16 — Telegram Notifications

Bot: @RatalGroupBot. Token in Supabase Vault. Employee activates once by messaging bot. Chat ID stored in Employee DB.

| Trigger | Recipients |
| --- | --- |
| Expense / Food / OT submitted | → Employee (acknowledgement) |
| Car Maintenance submitted | → Department Head |
| Money Request raised / approved / rejected | → Dept Head ¦ Accounts ¦ Requestor (as applicable) |
| Funds sent to ANB-77 / ANB-39 | → Dept Head (RECEIVING prompt) |
| Job COMPLETED by DH | → Accounts (invoice ready) |
| Payroll processed / Bank transfer completed | → Each employee |
| Loan EMI due (1 week before) | → Employee |
| Compliance alert triggered | → Admin |

# Section 17 — Car Management

Car DB: CarID | PlateNumber | Make | Model | Year | Color | Department | AssignedToEmployeeID | RegistrationExpiry | InsuranceExpiry | MVPIExpiry | Status (ACTIVE / WORKSHOP / RETURNED / WRITTEN_OFF). Fuel tracked via Expense form + Car# auto-link.

# Section 18 — Bank Accounts

| Account | Entity | Purpose |
| --- | --- | --- |
| ANB-18 | ALL | Common salary account — WPS Bank Portion transfers |
| ANB-15 | ACCSYS | Main operating: customer receipts + operations payments |
| ANB-77 | ACCSYS | TISU operations (funded from ANB-15) |
| ANB-39 | ACCSYS | NISU / ITSU / CISU shared operations (from ANB-15) |
| ANB-29 | RAT | Cash salary + cash payments |
| ANB-13 | RAT | Incoming receipts + Overdraft (SAR 1M limit) |
| ANB-11 | GWT | All GWT transactions |
| CASH-001 | ACCSYS | Main Petty Cash |

# Section 19 — Dashboards (All Entities — Role-Based)

User sees ONLY data their role and entity permit. KPI cards clickable → drill-down. Supabase realtime subscriptions.

## 19.1  RAT Dashboard (Blue #1565C0)

| Group | KPI Cards |
| --- | --- |
| A — Today | Tickets Issued Today ¦ Fares Collected Today ¦ Commission Earned Today ¦ Agents Active Today |
| B — Monthly | Tickets This Month (vs last month %) ¦ Total Fares ¦ Commission ¦ VAT Collected ¦ BSP Net Remittance Pending |
| C — Outstanding | Customer Outstanding ¦ Credit Customers Overdue ¦ Refunds Pending |
| D — Alerts | Compliance Expiring ¦ Engagement Today ¦ Cash Balance (ANB-29/ANB-13) |

Travel Agent restricted view: own tickets/fares/commission only. No financials. No other agent data.

## 19.2  GWT Dashboard (Green #2E7D32)

Same structure as RAT with GWT entity filter. Bank balance shows ANB-11.

## 19.3  ACCSYS Dashboard (Purple #5A32D4)

| Group | KPIs | DH Sees | PM Sees |
| --- | --- | --- | --- |
| A — Approvals Needed | MRs Awaiting DH ¦ MRs Awaiting Finance ¦ Pending POs ¦ Jobs Complete — Invoice Not Raised ⚠️ | Own dept | Own projects |
| B — Project Overview | Active Projects ¦ Jobs In Progress ¦ Jobs Completed This Month ¦ Budget vs Actual Bar | Own dept | Own projects |
| C — Financial | AR Total ¦ AP Total ¦ Contract Value ¦ ANB-15/77/39 Balances | HIDDEN | HIDDEN |
| D — Alerts | Compliance Expiring ¦ Payroll Status ¦ Engagement Today ¦ MRs Awaiting RECEIVED | Own dept | HIDDEN |

## 19.4  Field Employee Mobile Dashboard

"Good morning [Name]" | My Submissions (last 10 + status) | Large buttons: [Expense] [OT] [Food] | My Loan Balance | Notification count.

# Section 20 — Employee Engagement (Mandatory)

| Status | Capture Method |
| --- | --- |
| AT_SITE | Job Activator check-in + GPS (200m radius outdoor) |
| AT_OFFICE | Auto-capture: device GPS enters office geofence (50m) → ARRIVAL. Exits → DEPARTURE. Silent. |
| MEETING_OUT | "Meeting Out" tap with destination. Manual. |
| ABSENT / LEAVE / HOLIDAY | System-derived from records |

Privacy: GPS active 07:00–20:00 only. No real-time tracking — geofence entry/exit events only.

# Section 21 — Integrations

| Integration | Status | Notes |
| --- | --- | --- |
| WPS File (ANB) | DONE | Format documented in Appendix A |
| Excel VBA Accounts + Payroll | DONE | Both systems analysed |
| Telegram Bot API | IN PROGRESS | @RatalGroupBot — employees activating |
| Amadeus CSV Import | PENDING | Mahmood to provide sample CSV |
| ZATCA Phase 2 | POST GO-LIVE | Currently ENZAPPs |
| WhatsApp MIS API | ON HOLD | Kept as fallback |

# Section 22 — Open Questions

| # | Question | Status |
| --- | --- | --- |
| Q1 | Hotels / Car Rentals for RAT/GWT? | OPEN |
| Q3 | Site Survey photo categories per dept | → PHASE 2 SCOPING |
| Q5–Q7 | GPS registration ¦ Additional compliance ¦ Telegram triggers | ALL RESOLVED |
| Site Master Q1–Q10 | All 10 Site Master open questions — see Part Two §8 | ALL RESOLVED — Part Two §8 |

# Section 23 — All Confirmed Decisions

| Topic | Decision |
| --- | --- |
| Entity 3 name | ACCSYS (final) |
| CISU full name | Civil Infrastructure Services Unit |
| GOSI base | Bank Portion (NOT Basic salary) |
| Saudi GOSI | 9% lump sum — company pays all, zero employee deduction |
| Expat GOSI | 3% of Bank Portion, company-borne |
| OT calculation + max | Basic ÷ 30 ÷ 8 × 1.5 ¦ 60 hrs/month system cap ¦ auto-feeds payroll |
| Food Allowance | Separate advance — NOT in payroll ¦ Remote site only ¦ SAR 30 or SAR 20/day |
| Loan eligibility | Ratal Sponsored + TRAVELS only ¦ from Cash Portion ¦ max 24 months |
| Penalty cap | 10% of SalaryPackage/month ¦ carry-forward ¦ Cash Portion only |
| Family ticket timing | Any time — no link to employee vacation ¦ once/year per dependent |
| DH / GM family | DH: wife + 3 kids, home country ¦ GM: wife + 4 kids, any destination |
| Field staff login | Session token — mobile# + PIN once, auto thereafter |
| Invoice reference | Contractor PO# always (End Customer Job# is additional reference) |
| Outgoing PO format | ACC-PO-XXXX + Date (Ratal → sub-con / supplier) |
| Site Master scope | 1 Job# = 1 SM (NISU) ¦ 1 Tower = 1 SM (TISU) ¦ 1 Charter = 1 SM (ITSU) |
| Budget lock rule | LOCKED after Dept Head + Finance approval — not editable |
| Variations | Tracked in Actual only — budget NOT amended |
| Payment terms | Per party by category — stored at Party record level |
| Ledger auto-posting | YES — every transaction auto-posts |
| Single entry principle | One entry point — no duplicate recording |
| ZATCA Phase 2 | No fixed date — post go-live |
| Site Survey | Phase 2 (full enterprise) ¦ Inventory: Phase 3 ¦ EDLMS: Phase 3 |

# Section 24 — Build Sequence (Phase 1 — July 31 Target)

| Week | Dates | Deliverables |
| --- | --- | --- |
| Week 1 | Jul 5–11 | DB schema. Employee form (all fields). Payroll (GOSI, cash/bank, auto-OT). WPS. Loans + Penalties + EOS. Unpaid vacation + levy. |
| Week 2 | Jul 12–18 | Vacations + Ticket Log. Business Trip. Accounting: Ledger, Journal, Contra, Payments, Receipts, Invoice + Contractor PO binding. Day Book + VAT. Travel: Tickets, Amadeus, BSP, Refunds. |
| Week 3 | Jul 19–25 | ACCSYS: Projects + Jobs + Contractor hierarchy + Job Activator. PO Request ¦ Money Request (8-stage) ¦ PM Budget. Budget vs Actual. Sub-cons + Vendors. All 15 Dept Statements. All 16 Travel Reports. Payroll Reports A,B,C. Compliance Alerts. |
| Week 4 | Jul 26–31 | Field Apps (mobile URLs). Basic Site Survey + Site Status. Employee Engagement (auto-capture). GPS Attendance. Telegram integration. All 3 dashboards (role-based). Full UAT + go-live. |
| Post Go-Live | Aug 2026+ | Site Master module (full spec in Part Two). ZATCA Phase 2. Phase 2: Enterprise Site Survey. Phase 3: Inventory + EDLMS. |

# Section 25 — UI/UX Design Guidelines

Philosophy: "Forms should be elegant. Dashboard should be organised and clean." Every screen must be pleasant with minimal effort.

## 25.1  Colour Scheme

| Entity | Primary | Secondary | Light BG |
| --- | --- | --- | --- |
| RAT | #1565C0 | #1E88E5 | #E3F2FD |
| GWT | #2E7D32 | #43A047 | #E8F5E9 |
| ACCSYS | #5A32D4 | #7C4EF5 | #EDE7F6 |
| Common | #FFFFFF background | Cards: #F8F9FC ¦ Text: #1E2A3A | Borders: #E8EAF0 |

## 25.2  Form Standards

Desktop: 2-column grid | Mobile (<768px): single column | Card with soft shadow

Labels ABOVE inputs | Auto-filled fields: coloured + AUTO tag

Rounded inputs: 8–12px | Required: asterisk (*) | Inline validation below field

Submit: entity colour gradient, min 44px height | Full RTL in Arabic

Success: shows Request# + "Telegram notification sent"

## 25.3  Dashboard Standards

KPI cards: white, soft shadow, 14px radius | Icon + trend + large number | Clickable → drill-down

Tables: zebra striping | Search + filter chips | Export PDF/Excel on every list

Status chips: PENDING=Amber | APPROVED=Green | REJECTED=Red | IN_PROGRESS=Purple

Mobile: sidebar → bottom tab bar | Tables → card-style rows

# Section 26 — Phase Roadmap

| Phase | Timeline | Scope |
| --- | --- | --- |
| Phase 1 — Core System | Jul 31, 2026 | Travel Agency (Tickets, BSP, Refunds, 16 Reports). Corporate (Projects, Jobs, POs, Money Requests). HR & Payroll (WPS, EOS, Loans). Accounting (Ledger, Invoices, VAT). Compliance. Dashboards. Field Apps. Telegram. |
| Phase 2 — Field Operations | Aug–Dec 2026 | Enterprise Site Survey: 18+ survey types, AI photo scoring, floor plan designer, equipment DB + auto BOQ, Google Earth for MW links, AutoCAD/PDF export, offline sync. Inventory foundation. |
| Phase 3 — Enterprise Operations | 2027 | Full Inventory + Asset Management (serial number, multi-warehouse, BOQ engine, delivery notes). EDLMS: 11-phase project lifecycle, document version control, digital signatures, MOP/PAT management. Full Procurement module. |
| Phase 4 — AI & Intelligence | 2027+ | AI photo analysis (blur, duplicate, OCR). Predict stock shortages + auto BOQ. Invoice anomaly detection. Budget overrun early warning. Cashflow prediction. Executive summary generation. |

Long-term vision: Unified Telecom ERP — CRM → Survey → BOQ → Procurement → Inventory → Execution → Finance → PAT/Handover → Maintenance → GIS → AI. Scalable to 1M+ surveys.

# Section 27 — Open Questions Tracker

| # | Question | Status |
| --- | --- | --- |
| Q1 | Hotels/Car Rentals for RAT/GWT? | OPEN |
| Q3 | Site Survey photo categories | → Phase 2 Scoping |
| Q5–Q7 | GPS ¦ Compliance ¦ Telegram | ALL RESOLVED |
| SM Q1–Q10 | All 10 Site Master questions | RESOLVED — Part Two §8 |

# Section 28 — Telegram Bot Setup Status

| Employee | Chat ID | Status |
| --- | --- | --- |
| Mahmood Shahbaz | 8767079512 | ✅ Active |
| Mohammad Rashad | 8069828682 | ✅ Active |
| Hafiz Shahzad | 8881636707 | ✅ Active |
| Umar Rahman | 6386454312 | ✅ Active |
| Raja Amjad | 1571319215 | ✅ Active |
| M Y A | 6564085867 | ✅ Active (identity to confirm) |
| Majid Parvez, Rehan Ul Haq, Khaled Khamis, Sulaiman ZTE, Tariq Aziz ZTE, Sattar Alamgir | — | ⚠️ Not yet activated — needs Telegram install |

Action: Share https://t.me/RatalGroupBot to remaining employees.

# Appendix A — WPS File Format (ANB Bank)

Confirmed from WPY25052026001.xlsx. Format: pipe-delimited text. Row 1 = Header (H). Rows 2+ = Detail per employee (D). Source account: ANB-18.

## A.1  Header Record (H)

| Col | Field | Value |
| --- | --- | --- |
| 1 | RecordType | 'H' |
| 2 | CompanyBankCode | 'ARNB' |
| 3 | BranchRefCode | 4237 |
| 4 | PaymentType | 'N' (Normal) |
| 5 | BatchReference | DDMMYYYY.001 |
| 6 | DebitAccountNo | ANB-18 account number |
| 7 | Currency | 'SAR' |
| 8 | ValueDate | DDMMYYYY (1 day after transaction) |
| 9 | TotalBatchAmount | Sum of all D-Col2 |
| 10 | TransactionDate | DDMMYYYY |
| 11 | EmployerRefNo | '1-92803' (MOL/GOSI) |
| 12 | Description | e.g. 'Salary For May 2026' |

## A.2  Detail Record (D)

| Col | Field | Value |
| --- | --- | --- |
| 1 | RecordType | 'D' |
| 2 | TotalAmount | Col7+Col8+Col9−Col10 |
| 3 | EmployeeIBAN | 24-char SA IBAN |
| 4 | EmployeeRef | e.g. 'EMP-001' |
| 5 | EmployeeBankCode | ARNB/RJHI/INMA/SABB/ALBI/RIBL/NCBK |
| 6 | Description | Same as H-Col12 |
| 7 | BasicAmount | Bank reporting (not real accounting) |
| 8 | HousingAmount | Bank reporting |
| 9 | OtherAmount | OT or additional |
| 10 | DeductionAmount | 0.00 normally |
| 11 | NationalID | Iqama# or Saudi National ID |

Rules: Include only WPSAllowed = YES AND BankPortion > 0. Exclude Outsource category.

# Appendix B — Contractor / Customer Classification Rules

| Term | Definition | Examples |
| --- | --- | --- |
| End Customer | Tier 1 — owns the network. NO direct Ratal contract. | STC, Mobily, Zain, TAWAL, Ministries, Banks |
| Contractor | Tier 2 — issues POs to Ratal. RATAL INVOICES THIS TIER. | Nokia, Cisco, Huawei, ZTE, SBM, BMC, MIS, Solutions |
| Ratal ACCSYS | Tier 3 — executes work. Issues ACC-PO-XXXX outward. | Ratal Group |

Invoice Rule: Always invoice Contractor (Tier 2) with Contractor PO# reference. End Customer Job# = additional reference only.

| Reference# | Exists For | Required On |
| --- | --- | --- |
| Job# / RFC# | STC, Mobily, Zain (telecom sector only) | Stored as additional reference — NOT on invoice |
| ContractorPONo | ALL projects | REQUIRED on every Ratal invoice |
| ACC-PO-XXXX | Ratal outgoing POs to sub-cons/suppliers | Required before any sub-con/supplier payment |

PART TWO

SITE MASTER & BUDGET VS ACTUAL FRAMEWORK

Operational & Financial Control Framework  |  NISU · TISU · CISU · ITSU  |  Version 2.0  |  All 10 Questions Resolved

RATAL GROUP

Travel & Corporate Management System

SITE MASTER & BUDGET VS ACTUAL

Operational & Financial Control Framework

Covering: NISU · TISU · CISU · ITSU

Version 2.0  |  July 2026  |  CONFIDENTIAL

All open questions resolved — ready for coding phase

# 1.  Executive Summary

Ratal Group delivers telecom and civil infrastructure services across Saudi Arabia as a sub-contractor to main contractors (Nokia, Huawei, Cisco, ZTE) whose end-clients are STC, TAWAL, Mobily, and Zain.

Revenue is earned against Contractor Purchase Orders (POs). Costs arise from sub-contractors, material suppliers, internal manpower, and field expenses. Today these are tracked in Excel VBA — fragmented across ledgers, payment forms, and journals with no real-time view of profitability per site or job.

This document (Version 2.0) incorporates confirmed answers to all 10 open questions raised in v1.0. It defines the final data model, business rules, and form specification for the Site Master module — the unified digital record binding the Contractor PO to every cost element for each site/job.

Key confirmed decisions:

- Site Master scope is one-to-one: 1 Job# (NISU) = 1 Site Master; 1 Tower (TISU) = 1 Site Master.

- Budget is locked on approval. Variations are tracked as actual cost overruns — budget is not amended.

- CISU spans five distinct work types, each with its own billing mechanism.

- ITSU bills per Charter (SOW). Client mechanisms vary.

- Ratal outgoing POs follow the format ACC-PO-XXXX. Contractor incoming POs are stored under the Purchase Orders tab.

- Payment terms are per-party by category, not a fixed standard.

# 2.  Business Model & Revenue Structure

## 2.1  The Contracting Chain

Ratal Group sits at tier 2 in a three-tier delivery chain:

| Tier | Party | Role |
| --- | --- | --- |
| Tier 1 | STC / TAWAL / Mobily / Zain | End Client — owns the network and sets the specification |
| Tier 2 | Nokia / Huawei / Cisco / ZTE (Main Contractor) | Prime Contractor — holds the main contract with end client; issues POs to Ratal Group. These POs are the revenue ceiling. |
| Tier 3 | Ratal Group (Sub-Contractor) | Executes field delivery; raises invoices to contractor; manages own sub-contractors and suppliers via ACC-PO-XXXX series. |
| Tier 4 | Ratal's Sub-Contractors & Suppliers | Specialised activity sub-cons and material suppliers. Each receives an ACC-PO issued by Ratal. |

## 2.2  PO Numbering — Confirmed

Two categories of POs exist in the system. They are fundamentally different:

| Type | Direction | Format | Where Stored |
| --- | --- | --- | --- |
| Contractor PO | INCOMING — Nokia/Huawei/ZTE issues to Ratal | Contractor's own ref# | Purchase Orders tab — "Incoming PO" record. This is the revenue document. |
| Ratal PO | OUTGOING — Ratal issues to Sub-Con / Supplier / Vendor | ACC-PO-0001 + Date | Purchase Orders tab — "Outgoing PO" record. Links to the Site Master it serves. |

✔  CONFIRMED: Ratal outgoing POs use the format ACC-PO-XXXX (e.g., ACC-PO-0001) with the issue date. Sequence is global across all entity types.

## 2.3  Revenue Recognition per Unit Type

| Unit | PO Pattern | Billable Trigger | Confirmed |
| --- | --- | --- | --- |
| NISU | Model-based BOQ — PO per model type (not per Job#) | Document Approval after PAT | 1 Job# = 1 BOQ model = 1 Site Master |
| TISU | One PO per tower | Handover milestone complete | 1 Tower = 1 PO = 1 Site Master |
| CISU | Varies by work type (see §3.3) | Per Contractor PO qty & terms | Billing = PO quantity + contractor terms |
| ITSU | Per Charter / SOW | Charter milestones / client mechanism | 1 Charter (SOW) = 1 Site Master |

# 3.  The Four Service Units — Confirmed Scope

## 3.1  NISU — Network Infrastructure Services Unit

✔  CONFIRMED: Each Job# maps to exactly one BOQ model type. Therefore: 1 Site Master = 1 Job# = 1 BOQ model at 1 physical site.

### How the NISU PO + Job# relationship works

The Contractor issues one PO covering a model type across many quantities. Ratal then receives individual Job# references for each installation. Example:

| Contractor PO Line | Qty | Unit Price | Total | Job# Allocation |
| --- | --- | --- | --- | --- |
| PE-Agg Model-1 (ASR-9922 2×100G, 2×40G, 2×10G) | 30 | SAR 65,000 | SAR 1,950,000 | 30 separate Job# → 30 Site Masters |
| PE-Agg Model-2 (ASR-9922 3×100G, 1×40G, 2×1G) | 42 | SAR 75,000 | SAR 3,150,000 | 42 separate Job# → 42 Site Masters |

The Contractor PO total (e.g., SAR 1,950,000 for 30 units) is the revenue envelope. Each Site Master carries the per-unit value (SAR 65,000) as its revenue ceiling.

### NISU Delivery Milestones

| # | Milestone | Responsible | Gate? | Notes |
| --- | --- | --- | --- | --- |
| 1 | Site Survey | NISU Survey Team |  |  |
| 2 | Floor Plan Approval | Client / Contractor | GATE | Installation cannot start without this |
| 3 | Power Approval | Facility / Client | GATE | Power cabling cannot proceed |
| 4 | MOP Submission | NISU Technical Team |  | Covers active + passive components |
| 5 | MOP Approval | Contractor / Client | GATE | Installation start clearance |
| 6 | Passive Material Procurement | Procurement / Suppliers |  | PO ACC-PO-XXXX to supplier; triggers supplier ledger |
| 7 | Installation | NISU Field Team |  | Active equipment delivered by contractor at no cost to Ratal |
| 8 | PAT | PAT Team + Contractor | GATE | Pre-Acceptance Test; document submission trigger |
| 9 | Document Submission | NISU Admin |  |  |
| 10 | Document Approval | Contractor | GATE | Invoice eligibility unlocked |
| 11 | Invoice Submission | Finance |  | Revenue recognition event |

### NISU Passive Material Procurement — Example (10 sites)

| Supplier | Material | Qty | Unit Price | PO Value |
| --- | --- | --- | --- | --- |
| MOUSA Cables | Power Cable 35mm | 8,000 m | SAR 23 | SAR 184,000 |
| Schindler Electrics | Circuit Breaker | 320 units | SAR 60 | SAR 19,200 |
| Smart Communications | Cabinet 600×600 | 10 units | SAR 3,200 | SAR 32,000 |
| Smart Communications | Cabinet 800×1200 | 10 units | SAR 5,200 | SAR 52,000 |
| MDX Suppliers | Cable Ladder | 150 pieces | SAR 240 | SAR 36,000 |

## 3.2  TISU — Tower Infrastructure Services Unit

✔  CONFIRMED: One Contractor PO per tower. Each tower is a standalone Site Master. Cluster POs not currently used — policy may be revisited in future.

### Tower Classification & Revenue per Site Master

| Tower Type | Heights (m) | Client Example | PO per Tower | Site Master Revenue |
| --- | --- | --- | --- | --- |
| 4-Leg Lattice | 45 / 60 / 75 / 90 | TAWAL | 1 PO = 1 SM | SAR 140,000–180,000 |
| 4-Leg Lattice (Zain) | 60 | Zain | 1 PO = 1 SM | SAR 150,000 |
| Monopole | 30 / 45 / 60 | Urban sites | 1 PO = 1 SM | Varies |
| Tri-Leg | 45 / 60 | Rare | 1 PO = 1 SM | Varies |

### TISU 15-Step Milestone Checklist

| # | Milestone | Executor | Gate? | Sub-Con Pool / Notes |
| --- | --- | --- | --- | --- |
| 1 | Site Survey | NISU Survey Team |  | Soil + access route assessment |
| 2 | Design Review | Structural Engineer | GATE | Authority/client approval required |
| 3 | Excavation | Sub-Con Pool (5–8) |  | Rate varies: 45m tower SAR 20k, 65m SAR 25k; per region |
| 4 | Lean Concrete | Sub-Con / Own Team |  | Levelling layer before foundation |
| 5 | Compaction | Sub-Con Pool (5–8) |  | Certification required |
| 6 | Back Filling | Sub-Con / Own Team |  | After foundation curing |
| 7 | Testing & Certification | Sub-Con Pool (4–6) |  | Compaction + torque tests |
| 8 | Foundation | Sub-Con Pool (4–6) |  | Rebar + concrete; 28-day cure minimum |
| 9 | Tower Transportation | Transport Sub-Con |  | Heavy vehicle; permit per dimensions |
| 10 | Tower Erection | Sub-Con Pool (5–10) | GATE | Crane required; HSE plan mandatory |
| 11 | RFI | Quality Team |  | Formal inspection request to client |
| 12 | Power Cabling | TISU Electrical Team |  | Generator / grid connection |
| 13 | Fencing | Sub-Con Pool |  | Security perimeter |
| 14 | PAT | PAT Team + Contractor | GATE | Pre-Acceptance Test |
| 15 | Handover | Project Manager | GATE | Revenue recognition; invoice trigger |

## 3.3  CISU — Civil Infrastructure Services Unit

✔  CONFIRMED: CISU spans five distinct work types, each with its own billing mechanism. Billing in all cases is governed by the Contractor's PO quantity and payment terms. PM tracks all authority approvals.

CISU is the most diverse unit in scope. The Site Master data model must support multiple CISU work types under one department:

### CISU Work Type Matrix

| Work Type | Example | PO Pattern | Billing Mechanism |
| --- | --- | --- | --- |
| Microwave Links | MW antenna erection, waveguide, IDU, alignment | Cluster PO — multiple links per month | Per link commissioned within the cluster period |
| Node Installations | SBM: 8,000 nodes across sites | Bulk Qty PO (no Job# per node) | Quantity installed × unit rate from contractor PO |
| Camera Installations | CCTV, PTZ cameras, NVR | Unit Qty PO | Per camera installed and accepted |
| Door Access Systems | Card readers, control panels, barriers | Unit Qty PO | Per unit installed and commissioned |
| Data Centre Infrastructure | Raised floor, cabling, PDU, cooling, racks | Milestone / deliverable PO | Per phase milestone or deliverable acceptance |

For CISU, the Site Master ID reference (e.g., SM-CISU-26-003) is used when the contractor does not issue a specific Job# or site reference. For Microwave Links, the link ID (provided by contractor) is used as the Job# reference.

### CISU — Microwave Links: Cluster PO Logic

MW Links are issued as cluster POs covering all links scheduled within a billing period (typically monthly). Each cluster PO may cover 5–20 links. The Site Master is created per link; the cluster PO is referenced on all Site Masters within that batch:

- Cluster PO → references multiple Site Masters (one per link)

- Each link's Site Master carries: cluster PO#, link ID, allocated unit value

- Invoicing: all links in the cluster that reach "commissioned" milestone are invoiced together in one claim

- PM tracks permit status for each link independently (antenna permits, municipal clearances)

### CISU — Node/Camera/Door Access: Bulk Quantity Logic

For large-scale unit installations (e.g., SBM 8,000 nodes), there is no Job# per node. The Site Master is created per project batch:

- Site Master covers the entire batch or a deployment phase (e.g., "SBM Nodes Phase 1 — 2,000 units")

- Budget = unit cost × planned quantity

- Actual = unit cost × quantity installed to date (tracked via progress report)

- Invoice raised against quantity completed each billing period

## 3.4  ITSU — IT Services Unit

✔  CONFIRMED: ITSU bills per Charter (SOW document). 1 Charter = 1 Site Master. Different clients follow different billing mechanisms — the system must support flexible billing terms per Contractor PO.

### What is a Charter in ITSU context?

A Charter is equivalent to a Statement of Work (SOW) — it defines the scope, devices in scope, configuration standard, timeline, and acceptance criteria for a specific ITSU engagement. Examples:

- Charter: "Nokia — ASR Router Configuration, SAR Sites, Phase 2 — 120 devices @ SAR 1,200 each"

- Charter: "Huawei — Core Switch OS Upgrade — 45 switches, fixed price SAR 90,000"

- Charter: "Client XYZ — Network Audit & Configuration Review — 80 engineer-days @ SAR 1,500/day"

The billing mechanism varies by client. The system stores the billing type in the Charter/Site Master:

| Billing Type | Description | System Behaviour |
| --- | --- | --- |
| Per Device | Fixed price per configured device | Count devices marked "configured + tested"; multiply by unit rate |
| Fixed Price | One price for the full charter | 100% revenue on Charter acceptance |
| Per Engineer-Day | Day rate × actual days | Timesheet-driven; daily team allocation form feeds actual |
| Per Milestone | Payment at defined deliverables | Gate milestones in Charter determine invoice eligibility |

# 4.  The Site Master — Final Data Model

## 4.1  Site Master Identifier Logic

The identifier depends on whether the client/contractor provides a reference:

| Scenario | ID Used | Example |
| --- | --- | --- |
| Client provides Job# | Use client Job# as the primary reference field; system still generates SM-ID internally | Job# = STC-JOB-00123; SM-ID = SM-NISU-26-001 (cross-linked) |
| Client provides RFC# | Use RFC# as the primary reference; SM-ID generated internally | RFC# = TAW-RFC-0456; SM-ID = SM-TISU-26-047 |
| No client reference | Use system-generated SM-ID as primary | SM-ID = SM-CISU-26-003 (e.g., for node batch) |

The system always generates the SM-ID. The Job# / RFC# is a searchable cross-reference field. Users can search by either.

## 4.2  Site Master Hierarchy

| Level | Entity | Description |
| --- | --- | --- |
| Level 1 | Project (LOI / Contract) | Spans years; may contain hundreds of sites. E.g., "STC PE-Agg Expansion 2026". |
| Level 2 | Site Master (Job# / Tower / Charter) | 1 per revenue unit. Holds Contractor PO + budget + actuals + milestones. THE profit centre. |
| Level 3 | Cost Line Items | Individual ACC-POs to sub-cons/suppliers, expenses, manpower allocation, OT, FA. |

# 5.  Budget vs Actual — Confirmed Rules

## 5.1  Budget Lock Rule

✔  CONFIRMED: Once the budget is approved by Department Head + Finance, it is LOCKED. It cannot be edited. Variations (scope changes or unexpected costs) are NOT added to the budget — they appear as cost overruns in the Actual column. This is intentional: it reveals the true variance between the original plan and reality.

The workflow:

- Step 1: PM creates Site Master immediately on receiving Contractor PO.

- Step 2: PM fills in the budget breakdown within 48 hours (system warns after 48h if budget is still empty).

- Step 3: Dept Head + Finance approve the budget. Budget is now LOCKED (read-only).

- Step 4: PM can begin issuing ACC-POs against the Site Master. ACC-POs feed the Actual.

- Step 5: If additional costs arise (variation), they are raised as new ACC-POs. They increase the Actual, creating visible overrun — shown in the traffic light dashboard.

- Step 6: If the Contractor issues a Variation Order (additional scope = additional revenue), a new Contractor PO line is linked to the Site Master, increasing the revenue ceiling. A separate budget line for the VO is added (clearly labelled as VO).

## 5.2  What Feeds the Actual

| Source | How It Links | Timing |
| --- | --- | --- |
| ACC-PO (Sub-Con) | SM# on ACC-PO form | Committed on PO issue; payment updates ledger |
| ACC-PO (Supplier) | SM# on ACC-PO form | Committed on goods receipt; payment updates supplier ledger |
| Expense Claims | SM# on Expense form | On Finance approval |
| Overtime (OT) | SM# on OT form | On Dept Head approval; cost = hours × rate |
| Food Allowance (FA) | SM# on FA form | On Dept Head approval; daily rate × days allocated |
| Manpower / Payroll | Daily Allocation Form (see §5.3) | PM assigns team to SM Job# daily; monthly payroll × allocation % |
| Money Requests (MR) | SM# on MR form | On Finance approval; site-specific cash advance |

## 5.3  Daily Manpower Allocation Form

✔  CONFIRMED: PM allocates team members to Site Masters daily using a dedicated form. If the contractor has provided a Job#, the PM selects that Job# as the reference. If no Job# exists, the PM selects the system-generated SM reference. This feeds payroll cost into the correct Site Master.

Form fields:

- Date (defaults to today)

- Project # (dropdown — filters Site Masters below)

- Site Master / Job# (dropdown — all active Site Masters on the selected project)

- Employee (dropdown — active employees)

- Allocation % (e.g., 100% if full day on this site, 50% if split)

- Work Type (Field / Office / Remote / Travel Day)

- Remarks

The system calculates: Manpower Cost = (Monthly Salary / Working Days) × Days Allocated × Allocation %. This accumulates in the Actual against the Site Master.

## 5.4  Traffic Light Dashboard

| Signal | Trigger | System Action |
| --- | --- | --- |
| 🟢 GREEN | Actual < 70% of Budget | No action. Site tracking normally. |
| 🟡 AMBER | Actual 70–85% of Budget | Alert to PM. Review remaining milestone costs. |
| 🟠 ORANGE | Actual 85–95% of Budget | Alert to Dept Head. No new ACC-POs without Dept Head approval. |
| 🔴 RED | Actual 95–100% of Budget | Alert to Finance Director. PO issuance blocked pending review. |
| ⚫ CRITICAL | Actual > Budget (overrun) | Alert to GM. All new costs require GM approval. Contractor VO claim to be explored. |

# 6.  Party Ledger & Payment Terms

## 6.1  Payment Terms — Confirmed Model

✔  CONFIRMED: Payment terms are negotiated per party, by category. There is no fixed standard. Each Party List entry stores its own payment terms. Overdue alerts trigger based on the individual party's agreed terms.

Payment terms are stored at the Party record level (in the Party List). The structure:

| Category | Typical Range | Stored Where | Overdue Alert |
| --- | --- | --- | --- |
| CONTRACTOR (incoming PO) | 30–60 days after invoice | Party record — Contractor | Accounts Receivable overdue: invoice date + terms |
| SUB-CONTRACTOR | 30–45 days after site completion | Party record — Sub-Con | Accounts Payable overdue: completion date + terms |
| SUPPLIER | 15–30 days after goods receipt | Party record — Supplier | Accounts Payable overdue: GRN date + terms |
| VENDOR (general) | As negotiated | Party record — Vendor | Per agreed date |

## 6.2  Contractor PO — Partial Payment Handling

Contractors often pay in stages based on milestone completion (e.g., 60% on PAT, 40% on Handover). This is governed entirely by the Contractor's PO payment terms. The system handles this as follows:

- Contractor PO stores: payment schedule terms (e.g., "60% on PAT completion, 40% on handover acceptance")

- When a milestone gate is completed, the system prompts Finance: "Milestone [X] complete — SAR [amount] invoice can now be raised."

- Finance raises an invoice against the Site Master for the eligible amount.

- Revenue is recognised in the Site Master only when the invoice is raised (not on milestone completion).

- Payment receipt is recorded when the contractor remits — updating the Contractor ledger (Accounts Receivable).

## 6.3  Three Ledgers — Automatic Updates

Every financial transaction in the system updates one of three ledgers in real time:

| Ledger | Triggered By | Entries |
| --- | --- | --- |
| Contractor Ledger (AR) | Invoice raised against Site Master | DR Invoice Amount → Contractor; CR Revenue. On payment receipt: DR Bank, CR Contractor. |
| Sub-Con Ledger (AP) | ACC-PO issued to Sub-Con | DR Sub-Con Cost (on PO issue). On payment: DR Sub-Con, CR Bank. Overdue shown after terms date. |
| Supplier Ledger (AP) | ACC-PO + Goods Receipt | DR Cost on GRN date (not PO date). On payment: DR Supplier, CR Bank. Overdue by GRN date + terms. |

# 7.  Site Master Form — Final Field Specification

## 7.1  Header Fields (all units)

| Field | Type | Rules |
| --- | --- | --- |
| SM-ID | Auto (read-only) | Format SM-[UNIT]-[YY]-[SEQ]. Generated on create. Non-editable. |
| Client Job# / RFC# | Free text | Optional — contractor-provided reference. Cross-linked to SM-ID. Searchable. |
| Service Unit | Dropdown | NISU / TISU / CISU / ITSU. Determines milestone set shown below. |
| CISU Work Type | Dropdown (CISU only) | MW Links / Node Installation / Camera / Door Access / Data Centre |
| Project # | Linked dropdown | From Projects table. Sets entity + contractor context. |
| SOW# / Charter# (NISU/ITSU) | Free text | NISU: Statement of Work#. ITSU: Charter reference. |
| BOQ Model (NISU only) | Dropdown | PE-Agg Model-1 / Model-2 / custom — determines unit revenue |
| Tower Type (TISU only) | Dropdown | 4-Leg / Monopole / Tri-Leg |
| Tower Height (TISU only) | Dropdown | 30m / 45m / 60m / 75m / 90m |
| End Client | Dropdown | STC / TAWAL / Mobily / Zain |
| Contractor | Dropdown (Party List) | CONTRACTOR type only — Nokia / Huawei / Cisco / ZTE |
| Contractor PO # | Free text + Amount | Revenue ceiling for this SM. Linked to incoming PO record. |
| ITSU Billing Type (ITSU only) | Dropdown | Per Device / Fixed Price / Per Engineer-Day / Per Milestone |
| Region | Dropdown | Riyadh / Jeddah / Eastern / Makkah / Madinah / Other |
| Status | Dropdown | Open / Survey / Active / On Hold / PAT / Completed / Invoiced / Closed |
| Start Date | Date DD/MM/YYYY |  |
| Target Completion | Date DD/MM/YYYY | Used for schedule variance |
| Actual Completion | Date DD/MM/YYYY | Auto-set when final milestone is checked Done |
| Our PM | Dropdown (Employees) | Ratal PM from employee list |
| Our Supervisor | Dropdown (Employees) | Ratal Supervisor from employee list |
| Created By | Auto | Logged-in user |

## 7.2  Budget Section Fields

Filled by PM / Dept Head. Locked after approval. Budget vs Actual shown side-by-side. Categories adapt to the Service Unit type:

| Budget Category | Budget SAR | Actual SAR | Variance | Applies To |
| --- | --- | --- | --- | --- |
| Sub-Con — Excavation | — | — | — | TISU |
| Sub-Con — Compaction | — | — | — | TISU |
| Sub-Con — Foundation & Lean Concrete | — | — | — | TISU |
| Sub-Con — Tower Erection | — | — | — | TISU |
| Sub-Con — Fencing | — | — | — | TISU |
| Sub-Con — Testing & Certification | — | — | — | TISU / CISU |
| Sub-Con — Transportation | — | — | — | TISU |
| Sub-Con — MW / Antenna Works | — | — | — | CISU MW Links |
| Sub-Con — Other | — | — | — | All |
| Materials — Passive (cables, ODF, CBs) | — | — | — | NISU |
| Materials — Civil (steel, concrete, gravel) | — | — | — | TISU |
| Materials — RF / Waveguide | — | — | — | CISU MW |
| Materials — Other | — | — | — | All |
| Manpower — Internal (from daily allocation) | — | — | — | All |
| Manpower — ITSU Engineer-Days | — | — | — | ITSU |
| Food Allowance | — | — | — | All |
| Site Expenses | — | — | — | All |
| Overhead / Margin Provision (%) | — | — | — | All — % configurable per project |
| TOTAL BUDGET COST | — | — | — | Auto-sum |
| Contractor PO — Revenue | — | — | — | From PO field; read-only here |
| BUDGETED MARGIN (SAR / %) | — | — | — | Revenue minus Total Cost |

# 8.  Confirmed Decisions — Full Q&A Record

This section records all 10 open questions from v1.0 and their confirmed answers, for permanent reference.

| # | Question | Confirmed Answer |
| --- | --- | --- |
| 1 | NISU: does one Job# always map to exactly one BOQ model type? | YES — each Job# has its own BOQ. Therefore 1 Job# = 1 BOQ model = 1 Site Master. The Contractor PO covers all quantities of a model type; individual Job# references are the per-site identifiers. |
| 2 | TISU: one PO per tower, or cluster POs? | One PO per tower. 1 Tower = 1 PO = 1 Site Master. Cluster POs may be considered in future but are not currently in use. |
| 3 | CISU: billing milestone for MW links? | Billing per link commissioned within a cluster PO period. CISU also covers Node installations (bulk qty — e.g., SBM 8,000 nodes), Camera installations (unit qty), Door Access (unit qty), and Data Centre infrastructure (milestone/deliverable). All billing follows contractor PO quantity and payment terms. PM tracks authority approvals. |
| 4 | ITSU: billing per device, per project, or per engineer-day? | Billing per Charter (SOW). Each Charter defines the billing mechanism — this varies by client (per device, fixed price, per engineer-day, or per milestone). System stores billing type on the Site Master and applies accordingly. |
| 5 | Overhead: fixed % of revenue or fixed SAR per unit? | Margin must be built into the budget. Specific overhead % is to be defined per project by the PM / Finance at budget time. Field: "Overhead / Margin Provision (%)" — configurable per Site Master. System calculates actual margin automatically. |
| 6 | Payroll allocation: timesheet, fixed allocation, or PM decides? | PM decides daily, using the Daily Manpower Allocation Form. PM assigns each team member to a Site Master / Job# reference. If a client Job# exists, that is used. If not, the system-generated SM reference is used. Allocation % per day is PM-controlled. |
| 7 | Variation Orders: additive or deductive? | Any variation is tracked in the Actual — not added to the budget. Budget is locked once approved. A locked budget vs actual comparison is the correct way to measure variation (cost overrun = unplanned actual cost). If the Contractor issues a VO (additional revenue), a new PO line is added and a separate VO budget line is created — clearly labelled, not merged into the original budget. |
| 8 | CISU authority approvals: who tracks permit status? | PM tracks all authority permit status for CISU. Permit status is a blocking milestone in the Site Master — next activity cannot proceed until permit is marked as received. PM updates this field. |
| 9 | Partial payment from contractor: how is it handled? | Based on Contractor's PO payment terms. Contractor POs (incoming) are stored under the Purchase Orders tab. The PO record stores the payment schedule (e.g., 60% on PAT, 40% on Handover). When a milestone gate is completed, Finance is prompted to raise the eligible invoice amount. Ratal outgoing POs use format ACC-PO-XXXX + date. |
| 10 | Payment terms: standard across all parties or per party? | Per party, by category — not a fixed standard. Payment terms are stored at the individual Party record level in the Party List. Categories have typical ranges but each party negotiates individually. Overdue alerts trigger based on each party's specific agreed terms. |

# 9.  Sidebar Navigation & Enhancement Inputs

## 9.1  Sidebar Entry

| Group | Menu Item | Access |
| --- | --- | --- |
| Corporate | Projects | All with Corporate access |
| Corporate | Site Master ★ | SUPERADMIN, ADMIN, DEPT_HEAD, PROJECT_MANAGER |
| Corporate | → NISU Filter | NISU-specific view |
| Corporate | → TISU Filter | TISU-specific view |
| Corporate | → CISU Filter | CISU-specific view |
| Corporate | → ITSU Filter | ITSU-specific view |
| Corporate | Party List | SUPERADMIN, ADMIN, DEPT_HEAD |
| Corporate | Purchase Orders | SUPERADMIN, ADMIN, DEPT_HEAD, FIN |

## 9.2  Enhancement Inputs (Unchanged from v1.0)

- Milestone-Gated Invoicing: System blocks invoice creation until all gate milestones are marked Done with a document uploaded.

- Sub-Contractor Performance Rating: PM rates sub-con on quality, timeliness, safety, and pricing after each site — scores visible when assigning sub-cons to new Site Masters.

- Material Quantity Tracking: Budget stores quantity + unit price (not just total). Goods receipt records actual quantity. Wastage = ordered − installed, tracked per site.

- Cashflow Projection: Expected invoice date (milestone plan) vs sub-con/supplier payment due dates. Gap = site-level cashflow exposure. Aggregate = company cashflow requirement.

- PAT Document Repository: Required document types per milestone. A milestone cannot be marked Done without a document uploaded. Visible to Finance before invoicing.

- Payment Terms Ledger Integration: Sub-Con/Supplier ledgers auto-update on PO issue and payment. Contractor (AR) ledger auto-updates on invoice and payment receipt.

# 10.  Next Steps — Ready to Code

All open questions are resolved. The following sequence is recommended for the coding phase:

| # | Step | Scope |
| --- | --- | --- |
| 1 | SQL Migration | Add site_masters table + daily_allocations table + update purchase_orders for ACC-PO-XXXX pattern and incoming/outgoing distinction. Add SM# reference column to expenses, overtime_requests, food_allowances, money_requests. |
| 2 | Site Master Form | Build form per §7. Service Unit selector dynamically shows/hides fields. Auto-generate SM-ID. Link to Project + Contractor PO. |
| 3 | Milestone Module | Milestone checklist adapts to unit type. Gate enforcement. Document upload per milestone. Invoice prompt on gate completion. |
| 4 | Budget Section | Budget form with lock-on-approval workflow. Side-by-side Budget vs Actual. Traffic light dashboard. |
| 5 | ACC-PO Integration | Outgoing PO form: ACC-PO-XXXX numbering. Link each PO to a Site Master. PO issue updates sub-con/supplier ledger. |
| 6 | Daily Allocation Form | New form: Date + Project + SM/Job# + Employee + Allocation % + Work Type. Monthly payroll apportionment calculation. |
| 7 | Ledger Views | Contractor AR view, Sub-Con AP view, Supplier AP view. Overdue alerts per party terms. Aged payables report. |
| 8 | Site Master List View | Filter by unit / status / project / traffic light. Summary cards at top. Sortable columns. |
| 9 | Reports | Site Master P&L (per site). Project roll-up P&L. Overdue ledger. Budget burn report. Cashflow projection. |

Ratal Group — Site Master Framework v2.0  |  All Questions Resolved  |  July 2026  |  CONFIDENTIAL